## Sprint Backlog
Work Item / Task | Owner | Est. Effort | Status
PBI 1: Edit Resource (Metadata Input & Update) +1 | Team | 12h | To Do
Task: Design resource input/edit form (title, category, place, description) | Frontend | 4h | To Do
Task: Implement frontend validation for required fields | Frontend | 2h | To Do
Task: Implement backend API for resource creation and update | Backend | 3h | To Do
Task: Store and update metadata in database | Backend | 3h | To Do
PBI 2: Draft Management (Save & Load Draft) +1 | Team | 10h | To Do
Task: Implement 'Save Draft' button and draft UI logic | Frontend | 3h | To Do
Task: Load and display saved draft content | Frontend | 2h | To Do
Task: Implement backend draft-saving API | Backend | 3h | To Do
Task: Store draft status and data in database | Backend | 2h | To Do
PBI 3: Upload Resources (Files & Links) +1 | Team | 10h | To Do
Task: Integrate file upload component in resource form | Frontend | 3h | To Do
Task: Validate file format and link input (UI level) | Frontend | 2h | To Do
Task: Implement backend file upload handling | Backend | 3h | To Do
Task: Store uploaded file paths and link them to resources | Backend | 2h | To Do
PBI 4: Submit for Review (Workflow Transition) +1 | Team | 8h | To Do
Task: Implement 'Submit' button and submission flow | Frontend | 2h | To Do
Task: Validate required fields before submission | Frontend | 2h | To Do
Task: Update resource status to 'Pending Review' | Backend | 2h | To Do
Task: Prevent duplicate submission and lock editing | Backend | 2h | To Do
PBI 5: Revise and Resubmit Resource +1 | Team | 10h | To Do
Task: Display reviewer feedback/rejection reason | Frontend | 2h | To Do
Task: Enable editing of rejected resources | Frontend | 3h | To Do
Task: Implement resubmission logic (Rejected → Pending Review) | Backend | 3h | To Do
Task: Record resubmission history and status updates | Backend | 2h | To Do
Sprint Quality Assurance (Across all PBIs) | Team | 12h | To Do
Task: Unit testing for submission, draft, and upload logic | QA | 6h | To Do
Task: User Acceptance Testing (UAT) for full submission workflow | QA | 6h | To Do